## SAV. AV, SV, TPR
INSTITUTION:
VISIT TYPE:
| VISIT START DATE: | 00/00/00
WSCUC STAFF LIAISON:
| Please note that these dates are preferred dates but not inflexible. The dates of the visit and of the Commission review are fixed but all other dates may be adjusted. This timeline is to give you a sense of the sequence of events rather than to impose set dates. | [7 empty] | WSCUC staff reminder: Enter relevant data in cells C1, C3, C4. Enter dates in I38.
|  | TEAM MEMBERS |  | WSCUC STAFF |  | INSTITUTION STAFF | DATES
# | ACTION | Chair | Assistant Chair (AC) | Managers and/or Admin Staff | Vice President or Associate (VP) | Accreditation Liaison Officer (ALO) | OPTIMAL TIMELINE | TARGET DATE
BEFORE THE VISIT
1 | WSCUC sends preparation materials to ALO (team roster, timelines, draft schedules, logistics survey, email account information, hosting a visit guide) | - | - | Sends | Receives and reviews | Receives, acknowledges and reviews | 12 weeks before visit | #VALUE!
2 | WSCUC sends preparation materials to team (institutional and logistics information, team roster, timelines, worksheets etc.) | Receives and reviews | Receives and reviews | Sends | - | - | 12 weeks before visit | #VALUE!
3 | ALO sends the institution's report (for SAV and SV) or response to lines of inquiry (for AV) electronically to WSCUC, WSCUC provides link to team members. | Receives and reviews | Receives and reviews | Receives and reviews | Receives and reviews | Sends | 10 weeks before visit | #VALUE!
4 | WSCUC contacts the team to schedule pre-visit videoconference meeting | Provides availability | Provides availability | Arranges call | Provides availability | - | 10 weeks before visit | #VALUE!
5 | Chair sends first email to team with outline of team assignments and team worksheets | Sends | Receives and reviews | - | Receives and reviews | - | 8 weeks before visit | #VALUE!
6 | ALO emails the team and VP with the logistics survey and draft visit schedule | Sends and review | Receives and reviews | - | Receives and reviews | Sends | 7 weeks before visit | #VALUE!
7 | Team members send team worksheets to AC who will compile and distribute before the team meeting | Receives and reviews | Receives and compiles | - | Receives and reviews | - | 5-6 weeks before visit | #VALUE!
8 | Chair has a call with the CEO (the ALO/ VP/ AC may be included) | Leads call | May participate in call | May arrange call | May participate in call | May participate in call and should provide availability of the CEO | 5 weeks before visit | #VALUE!
9 | Team videoconference meeting is held | Leads call | Takes team notes | - | Participates in call | - | 4-5 weeks before visit | #VALUE!
10 | Chair or AC communicates with ALO as needed to finalize schedule, confirm requested documents, etc. | As needed | As needed | - | As needed | As needed | 4 weeks before visit | #VALUE!
11 | Institution sends notice of confidential email account to campus community | Notes receipt of notice | Notes receipt of notice | - | Notes receipt of notice | Sends notice, notifies VP | 3 weeks before visit | #VALUE!
DURING THE VISIT
12 | Team holds initial meeting | Leads team | Serves as team member and edits team draft report |  | Supports team | - | 4 pm on the day before the site visit starts | #VALUE!
13 | First day of site visit | Leads team | Takes notes and edits team draft report |  | Supports team on first 24 hours of visit or longer as needed | Provides logistical support and consultation | Meetings commence on site at 8-8.30 am | 00/00/00
14 | Last day of site visit | Leads team | Takes notes and edits team draft report |  |  |  | Meetings end at noon at latest | #VALUE!
AFTER THE VISIT
15 | WSCUC sends team chair and assistant chair deadlines for report completion process | Receives and reviews | Receives and reviews | Sends | Receives and reviews | - | 1 day after visit | #VALUE!
16 | Assistant chair sends consolidated draft report to team chair and VP | Receives and reviews | Sends | - | Receives and reviews | - | 1 week after visit | #VALUE!
17 | Team chair revises as necessary and sends first draft of report to team members and VP for review | Revises and sends | Receives and reviews | - | Receives and reviews | - | 2 weeks after visit | #VALUE!
18 | Team members submit expenses to WSCUC Finance Team for reimbursment | Sends | Sends | - | - | - | 2 weeks after visit | #VALUE!
19 | Team members and VP send comments to team chair | Receives and reviews, revises draft as needed | Sends comments; assists chair with report as needed | - | Sends comments | - | 3 weeks after visit | #VALUE!
20 | Team chair sends revised draft as PDF to institution for correction of errors of fact and redaction of proprietary information. Team chair also sends a copy to WSCUC | Sends | - | Receives and sends to VP and WSCUC President | Receives and reviews | Receives and reviews | 4 weeks after visit | #VALUE!
21 | Team chair sends confidential recommendation form to WSCUC | Sends | - | Receives and sends to VP, WSCUC President, Commission | Receives and reviews | - | 4 weeks after visit | #VALUE!
22 | Institution sends corrections and redactions to team report to team chair and VP | Receives and reviews | - | - | Receives and reviews | Sends | 6 weeks after visit | #VALUE!
23 | Chair revises report and sends final version to WSCUC and team members | Revises and sends | Receives and reviews | Receives and sends to VP, WSCUC President, Commission | - | - | 8 weeks after visit | #VALUE!
24 | WSCUC sends final team report to institution, and invites CEO to respond | - | - | Sends | Receives and reviews | Receives and reviews | 8-9 weeks after visit | #VALUE!
25 | CEO may respond in writing to the final team report; if so sends response to WSCUC | - | - | Receives and sends to VP, WSCUC President, Team Chair, Commission | - | Prompts CEO to send response if necessary | 2 weeks after receiving report/ 4 weeks before Commission meets (confirm with WSCUC staff)
26 | Commission reviews and takes action (Note: institutions are reviewed on the Wednesday or Thursday before this date) | Participates by conference call | Participates in call if the chair is unavailable | Attends Commission Meeting | Attends Commission Meeting | May participate in review (CEO is asked to participate by phone or in person and may invite other institutional representatives) | Institutions are reviewed during two days prior to target date, Commission meets on target date
27 | Team members destroy all institutional-related materials provided by the institution or by WSCUC | Shreds hardcopy documents, deletes electronic documents | Shreds hardcopy documents, deletes electronic documents | - | - | - | After Commission Action Letters are sent
28 | WSCUC sends action letter to the institution CEO, ALO, board chair and team members. Action letter and team report are published on WSCUC website. | Receives and reviews | Receives and reviews | Sends | - | CEO and ALO receive and review | 2-3 weeks after Commission meeting
28 | ALO distributes action letter and informs community of next steps | - | - | - | - | Distributes | Within 30 days after receiving action letter | #VALUE!
29 | Financial reconciliation | - | - | - | - | Receives bill for visit expenses from WSCUC Finance Team and arranges payment | 60 days after the visit | #VALUE!